EXP 9: CPM ANALYSIS

AIM:

To perform Critical Path Method (CPM) Analysis for project scheduling and management using Python.

PROCEDURE:

- Install Required Libraries:

  - Install pandas, networkx, matplotlib using pip.

- Define the Problem:

  - Identify tasks, durations, and dependencies.

- Set Up in Python:

  - Use NetworkX to represent tasks.

  - Perform topological sort.

- Run the Code:

  - Execute program to compute scheduling.

- Analyze Output:

  - Identify critical path and validate schedule.

CODE:

import networkx as nx
import matplotlib.pyplot as plt

tasks = {
'A': {'duration': 3, 'dependencies': []},
'B': {'duration': 2, 'dependencies': ['A']},
'C': {'duration': 4, 'dependencies': ['A']},
'D': {'duration': 2, 'dependencies': ['B']},
'E': {'duration': 3, 'dependencies': ['C']},
'F': {'duration': 1, 'dependencies': ['D', 'E']}
}

G = nx.DiGraph()

for task, data in tasks.items():
    G.add_node(task, duration=data['duration'])
    for dep in data['dependencies']:
        G.add_edge(dep, task)

topological_order = list(nx.topological_sort(G))

earliest_start = {task: 0 for task in topological_order}
earliest_finish = {task: 0 for task in topological_order}

for task in topological_order:
    earliest_finish[task] = earliest_start[task] + G.nodes[task]['duration']
    for successor in G.successors(task):
        earliest_start[successor] = max(earliest_start[successor], earliest_finish[task])

latest_finish = {task: earliest_finish[task] for task in topological_order}
latest_start = {task: earliest_start[task] for task in topological_order}

for task in reversed(topological_order):
    for predecessor in G.predecessors(task):
        latest_finish[predecessor] = min(latest_finish[predecessor], latest_start[task])
        latest_start[predecessor] = latest_finish[predecessor] - G.nodes[predecessor]['duration']

critical_path = [task for task in topological_order if earliest_start[task] == latest_start[task]]

print('Earliest start times:', earliest_start)
print('Earliest finish times:', earliest_finish)
print('Latest start times:', latest_start)
print('Latest finish times:', latest_finish)
print('Critical path:', critical_path)

OUTPUT:

Earliest start times: {'A': 0, 'B': 3, 'C': 3, 'D': 5, 'E': 7, 'F': 10}
Earliest finish times: {'A': 3, 'B': 5, 'C': 7, 'D': 7, 'E': 10, 'F': 11}
Latest start times: {'A': 0, 'B': 3, 'C': 3, 'D': 5, 'E': 7, 'F': 10}
Latest finish times: {'A': 3, 'B': 5, 'C': 7, 'D': 7, 'E': 10, 'F': 11}
Critical path: ['A', 'C', 'E', 'F']

RESULT:

The Critical Path Method was successfully implemented and the critical path was identified correctly.