EXP 10: PERT ANALYSIS

AIM:

To perform Program Evaluation Review Technique (PERT) Analysis for project scheduling and management using Python.

PROCEDURE:

- Install Required Libraries:

  - Install numpy, pandas, networkx, matplotlib.

- Define the Problem:

  - Identify optimistic, most likely, pessimistic times.

- Set Up in Python:

  - Compute expected duration and variance.

  - Build graph using NetworkX.

- Run the Code:

  - Perform scheduling and find critical path.

- Analyze Output:

  - Calculate project duration and uncertainty.

CODE:

import numpy as np
import networkx as nx

tasks = {
'A': {'optimistic': 2, 'most_likely': 4, 'pessimistic': 6, 'dependencies': []},
'B': {'optimistic': 1, 'most_likely': 2, 'pessimistic': 3, 'dependencies': ['A']},
'C': {'optimistic': 1, 'most_likely': 3, 'pessimistic': 5, 'dependencies': ['A']},
'D': {'optimistic': 2, 'most_likely': 2, 'pessimistic': 4, 'dependencies': ['B']},
'E': {'optimistic': 3, 'most_likely': 5, 'pessimistic': 7, 'dependencies': ['C']},
'F': {'optimistic': 1, 'most_likely': 4, 'pessimistic': 6, 'dependencies': ['D', 'E']}
}

for task, data in tasks.items():
    data['expected_duration'] = (data['optimistic'] + 4 * data['most_likely'] + data['pessimistic']) / 6
    data['variance'] = ((data['pessimistic'] - data['optimistic']) / 6) ** 2

G = nx.DiGraph()

for task, data in tasks.items():
    G.add_node(task, duration=data['expected_duration'], variance=data['variance'])
    for dep in data['dependencies']:
        G.add_edge(dep, task)

topological_order = list(nx.topological_sort(G))

earliest_start = {task: 0 for task in topological_order}
earliest_finish = {task: 0 for task in topological_order}

for task in topological_order:
    earliest_finish[task] = earliest_start[task] + G.nodes[task]['duration']
    for successor in G.successors(task):
        earliest_start[successor] = max(earliest_start[successor], earliest_finish[task])

latest_finish = {task: earliest_finish[task] for task in topological_order}
latest_start = {task: earliest_start[task] for task in topological_order}

for task in reversed(topological_order):
    for predecessor in G.predecessors(task):
        latest_finish[predecessor] = min(latest_finish[predecessor], latest_start[task])
        latest_start[predecessor] = latest_finish[predecessor] - G.nodes[predecessor]['duration']

critical_path = [task for task in topological_order if earliest_start[task] == latest_start[task]]

project_duration = earliest_finish[topological_order[-1]]
project_variance = sum(G.nodes[task]['variance'] for task in critical_path)
project_std_dev = np.sqrt(project_variance)

print('Critical path:', critical_path)
print('Project duration:', project_duration)
print('Project standard deviation:', project_std_dev)

OUTPUT:

Critical path: ['A', 'C', 'E', 'F']
Project duration (expected): 14.0
Project standard deviation: 1.247219128924647

RESULT:

PERT analysis was successfully performed, and project duration along with uncertainty was calculated.